Natural Resources Inventory Update

Kickoff Meeting Minutes

January 29, 2026

- Introductions – roles

  - Aimee introduced Broome County’s Climate Smart Community grant with NYSDEC

  - Consultant introductions

  - PAC team introductions

  - Aimee will update the PAC list and send out

- Review grant program requirements

  - Tasks and deliverables

    - Work plan with schedule of deliverables (parallel to DEC Work Plan)

      - Robbyn showed the Ecos Workplan

      - Aimee accepted this in current format, Robbyn will send

    - Regular project coordination meetings

    - Community Outreach and Engagement Plan – discussed below

    - Creation of a County Natural Resources Vision Statement

      - Robbyn proposed two Vision Statement options

      - Group discussed combining these options

      - Amanda (NYSDEC Grant administrator) said that this would be acceptable

      - Aimee will send around a Google survey to the PAC to receive input

    - NRI Report Update with a focus on chapters for geology and soils, water resources, habitats and wildlife, climate conditions and projections, and cultural resources and land use, open space, and smart growth opportunities

      - Recommendations, strategies and opportunities (Local Land Use and Zoning Planning and Policies, Trail and Recreation Opportunities, Economic Development and Tourism, Natural and Cultural Resources, Smart Growth, Open Space Conservation, and Habitat Connectivity)

      - Potential resilience, conservation, and adaptation projects and implementation strategies or actions advancing community vision

      - Robbyn discussed how 1) and 2) above will be incorporated into a revision of the recommendations section of the current NRI

    - Live public engagement meeting – suggested for May-June 2027

    - Final Project Summary Report

    - Quarterly project status reports

  - DEC Work Plan review – Aimee will circulate for review

- Review project schedule

  - Monthly or every two months check in with planning team –  <30 min

  - PAC meeting every 6 months

- Review project goals and deliverables – next steps

  - Data Collection/Review – Jenny discussed datasets

  - GIS Mapping, Spatial Analysis & Online Map Publication – Jenny showed web maps

  - Community Engagement - Robbyn

    - Community Engagement Plan – Robbyn deliver by March

    - Online survey – will include other municipalities as per Chris’ question

    - Character interviews – includes PAC members

    - Community meeting

  - Narrative Report Update - Robbyn